QUOTATION BREAKDOWN

Canaan ERP: Phase-by-Phase Project Value

| Prepared for | Canaan Global International (Client) |
| --- | --- |
| Prepared by | Independent Software Developer |
| Date | 03 October 2026 |

Note on how this document was built The original ₹2,50,000 quotation predates the detailed module-by-module quotation on file (Quotation2, ₹4,00,000 fully-built-system quote) and is not itself preserved as a standalone document. This breakdown reconstructs the Phase 1 baseline by working backwards from the confirmed original figure and the confirmed final figure of ₹4,07,000, using Quotation2's module list and the verified build history of the system as the source of truth for what was added and when. Every rupee figure attached to Phases 2 to 4 is an indicative allocation of the additional ₹1,57,000 in scope, not a reconstruction of individual historical invoices.

1.  Executive Summary

Canaan ERP began as a focused, single-platform system to digitize the core of Canaan Global International's transport operations: trip booking, basic documentation, basic invoicing, fleet records, and staff and driver management. Over the course of development, the operational reality of running a container-transport business surfaced requirements that a basic ERP could not support: multi-type automated invoicing with GST handling, a dedicated yard-collection workflow, tyre and maintenance lifecycle tracking, profitability analytics down to the per-trip and per-truck level, and the security, auditability, and production engineering needed to run a system that handles real driver payments, real customer invoices, and real business data every day.

| Item | Amount |
| --- | --- |
| Original quotation | ₹2,50,000 |
| Additional scope (Phases 2 to 4) | ₹1,57,000 |
| Final project value | ₹4,07,000 |
| Increase over original scope | 62.8% |

This document traces that journey in four phases, provides a complete feature inventory of the final system, and explains in plain business terms why scope growth of this kind reliably increases development cost.

2.  Phase 1: Original ERP Scope

Original quotation: ₹2,50,000

The original engagement was scoped as a basic, single-platform ERP: the minimum viable system to get Canaan's core trip operations off spreadsheets and onto a shared, real-time system.

Core modules

- Trip Management: booking a trip, assigning a driver and truck, tracking status through to completion.

- Documentation & Reconciliation (basic): recording trip-sheet data and linking it back to the original booking.

- Accounts & Invoicing (basic): one invoice type per trip, without the later GST and multi-invoice-type handling.

- Fleet / Truck Management: a master record of every vehicle and its key documents.

- Driver & Staff Management: master records for every driver and staff member.

- Attendance: daily attendance marking, without the later leave-approval workflow.

- Finance (basic): a simple ledger of driver and staff payments, without EMI tracking or compensation-type logic.

- Dashboards (basic): a single summary screen per login, not yet role-differentiated.

- Reports (basic): Excel export of raw records, without the analytics layer added later.

Users and roles

A small set of roles (Admin and Staff) with simple login-based access, with no granular, per-action permission model yet.

Database, platform, security and deployment

- Database: a MySQL schema covering the core entities (trips, trucks, drivers, staff, basic invoices).

- Platform: a single web application accessible from any browser, with no desktop app, mobile apps, or in-app chat.

- Security: basic login and password authentication with session-based access, not yet the hardened model described in Phase 4.

- Deployment: delivery to a single server, with no formal backup automation, monitoring, or disaster-recovery plan.

This is the baseline against which all subsequent scope growth is measured.

3.  Phase 2: Business Workflow Expansion

Once the core system was in use, it became clear that Canaan's operations involve more moving parts than a basic trip-to-invoice flow. This phase covers the requirements that surfaced from real operational use.

| Requirement | Feature Built | Business Purpose | Technical Impact | Cost Impact |
| --- | --- | --- | --- | --- |
| Yard staff need a dedicated way to process incoming trips | Yard Supervisor Workflow: trip-sheet collection, driver-advance verification, pending-collection alerts | Removes a manual, paper-based yard handover step; yard staff work from the same live data as everyone else | New role, new screens, new backend endpoints scoped to yard-only data | Medium |
| One invoice type wasn't enough for how Canaan actually bills | Multi-type Automated Invoicing: Tax Invoice, Bill of Supply, and Transport Memo, each with its own running number sequence, plus GST (CGST/SGST/IGST) and Driver Advance Bills | Matches real tax and billing requirements; avoids manual GST calculation errors | Three distinct document generators, each with its own numbering and tax logic, all reading the same trip data | High |
| Trip data needed more rigor before it reached accounts | Full Documentation & Reconciliation: diesel logging, KM variance checks, flagging of inconsistent entries, edit-approval routing | Catches data-entry errors and fuel or mileage anomalies before they reach billing | Cross-checks between trip-sheet fields, plus a formal approval routing layer | Medium to High |
| Customers, vendors, and pricing lived in scattered spreadsheets | Resource Hub: centralized customer, vendor, staff, and pricing-table management | One source of truth for every party the business deals with | New master-data module feeding every invoicing and trip-assignment screen | Medium |
| No formal record of who changed what | Approvals & Audit: edit and delete approval routing plus a system-wide audit log | Protects data integrity; every change to sensitive records is reviewable | An audit trail requires every write path to log through it, not just the record it touches | Medium |
| System-wide settings had no admin interface | Admin Settings: branches and expense rates | Lets the business configure the system without a developer | Configuration screens that feed calculations elsewhere (e.g. branch-based compensation %) | Low to Medium |
| PDF and Excel output was needed beyond raw exports | Structured PDF and Excel generation for invoices, LR / Consignment Notes, and collection records | Documents ready to print, email, or file, not just raw data dumps | Each document type needs its own layout engine, not a generic table export | Medium |

Phase 2 turned the system from records trips into running the actual paperwork of the business.

4.  Phase 3: Advanced Operations, Analytics & Automation

This phase covers the features that moved the ERP beyond CRUD screens into a genuine transport-management and decision-support system.

| Feature | Why It Required Additional Development |
| --- | --- |
| Tyre Management (inventory, fitment history, lifespan tracking, plus a full soft-delete, Deletion Approval, Tyre Archive, Restore or Permanently Delete lifecycle) | Not a simple table. It is a stateful lifecycle with its own approval workflow, mirrored across three linked screens and kept in sync in real time. |
| Fuel & AdBlue Tracking | Auto-synced from trip-sheet data rather than manually re-entered, so the module has to understand trip-sheet structure, not just store numbers. |
| Maintenance Management (repair logs, KM-based maintenance alerts, and an admin-configurable Maintenance Category and Repair Type system feeding a dependent dropdown on the Truck Maintenance form) | A genuinely dynamic form: the Repair Type options change based on which Maintenance Type (Category) was picked, and both are admin-editable, not hardcoded. |
| Diesel & Advance Management | Driver advances, outstanding-advance calculations, and expense reconciliation, all computed live from trip-sheet data rather than stored as static numbers. |
| Finance module (EMI tracking, recurring costs, and driver and staff compensation with a live Net Payable calculation: Driver Batta Amount minus Outstanding Advance, with trip-category-specific exclusion rules) | This formula touches trip data, trip-sheet data, and compensation-type configuration at once, and had to stay consistent across every screen that shows a Salary figure. |
| P&L & Profitability Analytics (per-trip and per-truck P&L, EMI-share and maintenance-cost amortization, Running Cost Calculator in Manual, Basic, and Advanced modes, Customer Route Analytics, Fleet Summary) | Analytics of this depth pulls and correctly weights numbers from nearly every other module. It is the most cross-module-dependent part of the system. |
| Role-Specific Dashboards (Admin, Finance, Fleet, Staff, Auditor) | Each role sees a different slice of the same live data, so the dashboard layer is built per role, not as one generic screen. |
| Driver Record & Salary Breakdown (Auditor-facing): per-driver trip history with expandable detail, a date-range Total Trips and Salary summary, and a Salary Breakdown with a numeric and a proportional visual explanation of each trip's salary | Purpose-built for a read-only audit role. Every figure has to be traceable and explainable on demand, which is a more demanding requirement than an editable data-entry screen. |
| Reports & Automated Cloud Backup | Scheduled, unattended backups must not corrupt the live database. That is a different engineering problem from an on-demand Excel export. |

Every item in this phase depends on data from at least two other modules being correct and current. This is the layer where the system stopped being a set of independent screens and became genuinely integrated.

5.  Phase 4: Production-Grade System, Security & Final Scope

The final phase covers everything required to turn a working system into one the business can safely run every day, with real money and real driver and customer data flowing through it.

Security

- Authentication and session management, hardened beyond the basic Phase 1 login.

- Role-based access control enforced per API endpoint, not just per screen, including least-privilege scoping (e.g. an Auditor can see driver salary aggregates without being granted the full Finance module).

- Read-only enforcement that holds under direct interaction, not just visual styling. Date pickers and number-spinner fields in read-only dialogs were hardened so a restricted role cannot edit data through a control that merely looks disabled.

- Input validation and protection against SQL injection and XSS.

- Secure file handling for uploaded documents (photos, licenses, compliance documents).

- A full audit log of sensitive changes (deletion requests, approvals, restores).

- Data-access restrictions that hold when modules overlap: a soft-deleted record must disappear from every screen that lists it, not just the one it was deleted from.

Infrastructure

- Production deployment to the live server.

- Database schema managed through idempotent migrations: every schema change (new columns, new tables, widened enum values) runs safely against a live database with existing data, without a manual, risky one-off script.

- Environment configuration separating development from production.

- A defined backup strategy for disaster recovery.

Production engineering

- Systematic error handling and input validation across every form and API endpoint, not just the happy path.

- Performance work, e.g. lazy, concurrency-limited fetching of trip-sheet detail so pages with hundreds of records stay responsive.

- Resilience patterns: a page that depends on a role-gated data source is built so one blocked request does not blank the whole screen for that role.

- Real, disposable-data testing against the live database before any new workflow is trusted. Destructive operations are never tested against real business records.

- Ongoing bug fixing and refinement based on real usage, not just the original spec.

- Production support and responsiveness to issues found after go-live.

Final ERP scope

By the end of this phase, Canaan ERP is a role-based, real-time, production-hardened transport-management platform covering the complete operational, financial, and compliance lifecycle of the business, not the basic trip-tracking tool originally quoted.

6.  Complete Feature Inventory: Final System

| Module | Feature | Description | Business Purpose | Complexity |
| --- | --- | --- | --- | --- |
| Trip Management | Booking & Assignment | Create a trip, assign driver and truck, set container and cargo details | Central entry point for every job the business runs | Medium |
|  | Live Status Tracking | Trip status updates in real time across every screen | Everyone sees the same, current picture | Medium |
|  | Verification & Closure | Booking-sheet closure workflow with review before completion | Ensures a trip is not marked done with incomplete data | Medium |
| Documentation & Reconciliation | Trip Sheet Entry | Diesel, expenses, advances, KM readings per trip | Captures everything needed to compute cost and driver pay | High |
|  | KM Variance Checks | Flags inconsistent odometer readings | Catches data-entry errors before they reach accounts | Medium |
|  | Edit-Approval Routing | Changes to closed records require approval | Protects finalized data from silent edits | Medium |
| Accounts & Invoicing | Tax Invoice / Bill of Supply / Transport Memo | Three distinct, separately numbered document types | Matches real billing and tax requirements | High |
|  | GST Handling (CGST/SGST/IGST) | Automatic tax calculation on invoices | Removes manual tax-calculation error | High |
|  | LR / Consignment Note Generation | Structured shipping documents | Required paperwork for cargo movement | Medium |
| Yard Supervisor Workflow | Trip-Sheet Collection | Dedicated intake screen for yard staff | Digitizes a previously paper-based handover | Medium |
|  | Driver-Advance Verification | Cross-checks advance amounts on collection | Prevents advance-reconciliation disputes | Medium |
|  | Pending-Collection Alerts | Flags trips awaiting yard action | Nothing falls through the cracks | Low |
| Fleet / Truck Management | Vehicle Master Records | Full vehicle detail per truck | Single source of truth for fleet data | Low |
|  | Document Expiry Alerts | Insurance, permits, FC, and PUC tracked with alerts | Avoids compliance lapses and fines | Medium |
| Tyre Management | Tyre Inventory & Fitment History | Per-tyre lifecycle from purchase to removal | Tracks tyre cost and lifespan accurately | Medium |
|  | Soft-Delete / Archive / Restore Workflow | Deletion Approval, then Tyre Archive, then Restore or Permanently Delete | Prevents accidental, unreviewed data loss | Medium to High |
| Fuel & AdBlue | Fuel Log Auto-Sync | Pulled from trip-sheet data, not re-entered | Removes duplicate data entry and drift | Medium |
|  | AdBlue Purchase & Consumption Tracking | Logs AdBlue use alongside fuel | Complete running-cost picture | Low |
| Maintenance | Repair Logs & Costs | Full maintenance history per truck | Basis for maintenance-cost analytics | Medium |
|  | KM-Based Maintenance Alerts | Automatic reminders based on mileage | Prevents missed scheduled maintenance | Medium |
|  | Maintenance Category / Repair Type Management | Admin-configurable categories, each with its own repair types | Keeps the Truck Maintenance form's dropdowns accurate without developer involvement | Medium |
| Driver & Staff Management | Master Records | Photos, documents, and contact detail per person | Central HR-style record | Low |
|  | Role-Based Access | Each person's system access matches their job | Prevents over-permissioning | Medium |
| Attendance & Leave | Daily Attendance | Marking and monthly reporting | Replaces manual attendance registers | Low |
|  | Leave Requests & Approvals | Formal request, then approval routing | Auditable leave records | Low |
| Finance | EMI Tracking | Truck loan schedules and payments | Ties fleet cost to financial planning | Medium |
|  | Driver/Staff Compensation | Salary and advance tracking, with live Net Payable calculation | Accurate, formula-driven pay figures, not manual computation | High |
| P&L & Profitability Analytics | Per-Trip / Per-Truck P&L | Profitability broken down by trip and by vehicle | Shows exactly where the business makes or loses money | High |
|  | Running Cost Calculator (Manual / Basic / Advanced) | Per-km cost breakdown across EMI, fuel, tyres, and maintenance | Data-driven pricing and route decisions | High |
|  | Customer Route Analytics | Profitability by customer and route | Identifies the business's most valuable relationships | Medium |
| Dashboards | Role-Specific Dashboards | Admin, Finance, Fleet, Staff, and Auditor each see a tailored view | Relevant information only, no clutter | Medium |
| Resource Hub | Customers, Vendors, Staff, Pricing Tables | Centralized master data | One source of truth feeding every other module | Medium |
| Admin Settings | Branch Configuration, Expense Rates | System-wide configuration screens | Business can self-configure without a developer | Low to Medium |
| Reports & Backup | Excel Export | Structured data export | Feeds external reporting and accounting needs | Low |
|  | Automated Cloud Backup | Scheduled, unattended backup of system data | Protects against data loss | Medium |
| Approvals & Audit | Edit / Delete Approval Routing | Sensitive changes require review | Prevents silent, unreviewed data changes | Medium |
|  | Full Audit Log | Every significant action is logged | Accountability and traceability | Medium |
| Driver Record (Auditor) | Date-Range-Scoped Trip & Salary Summary | Per-driver trip count and salary for a selected period | Read-only oversight view for audit purposes | Medium |
|  | Salary Breakdown (Visual + Numeric) | Per-trip explanation of how salary was computed | Makes a formula-driven figure fully explainable, not a black box | Medium |
| System Foundation | Real-Time Sync | Every screen reflects live data via WebSockets | No stale data, no manual refresh needed | High |
|  | Authentication & Session Security | Hardened login and session handling | Protects the system's entry point | Medium |
| Security & Hardening | Role-Based API Access Control | Every endpoint checks the caller's role, not just the screen | Prevents access via direct API calls, not just UI restriction | High |
|  | Read-Only Enforcement | Disabled controls are genuinely non-interactive, not just styled that way | Closes the gap between looks locked and is locked | Medium |
|  | Input Validation & Injection Protection | Guards against malformed or malicious input | Protects data integrity and system security | Medium |
|  | Audit Trail | Logged history of sensitive actions | Supports accountability during disputes or reviews | Medium |
| Production Engineering | Idempotent Database Migrations | Schema changes apply safely to a live, populated database | Zero-downtime, zero-data-loss schema evolution | Medium to High |
|  | Error Handling & Validation | Systematic handling across every form and endpoint | A production system fails gracefully, not silently | Medium |
|  | Performance Optimization | Lazy, concurrency-limited data fetching for large record sets | Keeps the system responsive as data volume grows | Medium |

7.  Price Evolution: ₹2,50,000 to ₹4,07,000

| Phase | Scope Added | Incremental Cost | Cumulative Cost |
| --- | --- | --- | --- |
| Phase 1 | Original ERP: core trip, basic invoicing, fleet, driver and staff, attendance, basic finance, dashboards and reports, single web app, basic security | Original | ₹2,50,000 |
| Phase 2 | Business Workflow Expansion: Yard Supervisor Workflow, multi-type invoicing with GST, full documentation and reconciliation, Resource Hub, Approvals & Audit, Admin Settings, PDF and Excel document generation | ₹45,000 | ₹2,95,000 |
| Phase 3 | Advanced Operations, Analytics & Automation: Tyre Management, Fuel & AdBlue, Maintenance Management, Finance and Compensation logic, P&L & Profitability Analytics, role-specific dashboards, Driver Record & Salary Breakdown, automated backup | ₹75,000 | ₹3,70,000 |
| Phase 4 | Production-Grade System, Security & Final Scope: full RBAC and API security hardening, read-only enforcement fixes, production deployment, idempotent migrations, error handling, performance work, production support | ₹37,000 | ₹4,07,000 |

Arithmetic check: ₹45,000 + ₹75,000 + ₹37,000 = ₹1,57,000, and ₹2,50,000 + ₹1,57,000 = ₹4,07,000. ✔

Indicative allocation The phase groupings and feature attributions above are accurate to what was actually built. The specific rupee split of the additional ₹1,57,000 across Phases 2 to 4 is a scope-weighted estimate for the purpose of this breakdown, not a reconstruction of individual historical invoices.

8.  From Basic ERP to Integrated Transport Management System

| Stage | Cost | What It Adds |
| --- | --- | --- |
| Initial requirement | Starting point | Digitize trip booking and basic records |
| Core ERP (Phase 1) | ₹2,50,000 | Real operations need real paperwork: GST invoices, yard handovers, audit trails |
| Operational workflows (Phase 2) | +₹45,000 | The business needs to see, not just record: tyres, maintenance, profitability, compensation |
| Analytics & automation (Phase 3) | +₹75,000 | Real money and real data demand a system that is genuinely safe to run daily |
| Security & production engineering (Phase 4) | +₹37,000 | Hardening that protects every module built in Phases 1 to 3 |
| Final integrated ERP | ₹4,07,000 | One platform covering the full business |

Each stage did not replace the one before it. It sat on top of it. The trip-booking flow from Phase 1 is still the foundation every later module reads from, and Phase 4's security hardening protects every module built in Phases 1 to 3, not just the newest ones.

9.  Why ERP Development Cost Increases With Scope

A common client question is: Why does adding what sounds like one small thing cost real money? The honest answer is that almost nothing in a connected system is really one small thing. A single visible change typically touches several layers:

Database, Backend, API, Validation, UI, Reports, Calculations, Testing

A concrete example from this system

Adding the Repair Type field to the Truck Maintenance form (Phase 3) sounds like adding one dropdown. In practice it required:

- Database: a new column on the maintenance-records table, added through a live, data-safe migration.

- Backend: new fields on the create and update logic for maintenance records.

- API: new endpoints to manage the Maintenance Category and Repair Type lists, so the dropdown options are admin-editable rather than hardcoded.

- Validation: a Repair Type can only be picked once a Maintenance Type (Category) is selected, and it must belong to that category.

- UI: a dropdown whose options change based on another field's value, and reset correctly when that field changes.

- Reports: the new field flows correctly into any export or record view that shows maintenance history.

- Testing: verifying the whole chain against real but disposable data before trusting it with real records.

Multiply that pattern across dozens of features (Tyre Management's soft-delete lifecycle, the Salary Breakdown's live formula, GST-aware invoicing) and the reason scope growth costs real development time becomes concrete rather than abstract.

What each layer involves, in business terms

| Layer | What It Involves |
| --- | --- |
| Database design | Deciding how information is stored so it can be retrieved correctly and safely, for good |
| Backend development | The rules that decide what is allowed to happen (e.g. only an Admin can permanently delete a record) |
| API development | The communication channel between the visible screen and the stored data |
| Business logic | The formulas and rules specific to Canaan's operations (e.g. how driver salary is calculated) |
| UI development | What the user actually sees and interacts with |
| Reports & document generation | Turning stored data into something a person can read, print, or file with authorities |
| Security | Making sure only the right people can see or change the right data |
| Testing & debugging | Catching problems before they reach real business data |
| Deployment & production support | Getting the system running reliably, and keeping it that way |

10.  Final Project Summary

| Item | Value |
| --- | --- |
| Original quotation | ₹2,50,000 |
| Additional scope (Phases 2 to 4) | ₹1,57,000 |
| Final project value | ₹4,07,000 |
| Percentage increase | 62.8% |

Major categories responsible for the increase

- Multi-type, GST-aware automated invoicing and document generation

- A dedicated Yard Supervisor workflow

- Tyre and maintenance lifecycle management, including a full approval-and-archive workflow

- Profitability and running-cost analytics across trips, trucks, and customers

- Formula-driven, fully explainable driver compensation (Salary Breakdown)

- Production-grade security hardening and role-based API access control

- Production engineering: safe database migrations, error handling, and performance work

Final system scope

- 20+ integrated modules spanning trip operations, documentation, accounts, fleet, tyres, fuel, maintenance, HR and attendance, finance, analytics, and administration.

- Role-based access across Admin, Finance, Fleet, Staff, and Auditor views, each with a tailored dashboard and permission set.

- Real-time updates across every screen.

- Production-grade security: role-based API access control, genuinely enforced read-only restrictions, input validation, and a full audit trail.

- Deep analytics: per-trip and per-truck P&L, running-cost breakdowns, and customer and route profitability.

- Automation: document expiry alerts, KM-based maintenance alerts, auto-synced fuel logging, and automated cloud backup.

Why the final system is substantially larger than originally quoted: the original ₹2,50,000 scope answered the question how do we get trip records off spreadsheets? The final ₹4,07,000 system answers a much bigger question: how do we run and audit the entire transport business safely, from booking to payment to compliance, with confidence in every number the system shows us? That shift, not scope-padding, is what accounts for the difference.

Reference This breakdown should be read alongside Quotation2, which remains the most detailed module-by-module cost reference available for the final-scope system.

Independent Software Developer

Quotation Breakdown  ·  03 October 2026